PROJECT IMPLEMENTATION DOCUMENT

AI-Assisted Patient Workflow

Full Installation & Implementation Plan — Hashmanis Hospital, Karachi

Prepared for: Hospital Administration & IT Steering Committee

Document type: System Installation & Deployment Plan (SDLC-based)

Date: September 2026

Status: Draft v1.0 — For Review

Note: This document is a structured implementation proposal built for case-study / coursework purposes, based on the accompanying "AI-Assisted Patient Workflow" case study. Costs, durations and staffing figures are illustrative estimates, not vendor quotations.

# Table of Contents

# 1. Objective (Problem Statement)

Hashmanis Hospital is a multi-branch hospital group operating across Karachi. Its ophthalmology (eye care) departments handle a high daily patient volume that mixes true emergencies (sudden vision loss, chemical splashes, eye trauma) with routine, non-urgent check-ups. Under the current manual workflow, both categories compete for the same booking, check-in and waiting resources, which lengthens total visit time and delays care for patients who need it most urgently.

The objective of this project is to design, install and operationalise an AI-Assisted Patient Workflow system that:

- Automates booking, payment and check-in so front-desk time is minimised.

- Uses an AI triage engine to read patient symptoms, vitals and records at intake and automatically label each case as Emergency, Urgent or Routine.

- Routes patients accordingly, so emergency and urgent cases reach a doctor faster, while the treating physician always retains final authority to confirm or override the AI's recommendation.

- Reduces total time-in-system per visit without compromising clinical safety, data privacy, or doctor oversight.

Success is measured by a reduction in average visit duration (target: 15–36 minutes saved per visit depending on whether diagnostic eye tests are required — see Section 6), without any increase in missed or delayed emergency cases, and with 100% of AI triage decisions remaining reviewable and overridable by a licensed physician.

# 2. Methodology — Systems Development Life Cycle (SDLC)

This installation project is executed using the standard six-phase SDLC model. Each phase below maps to the corresponding project artefact required by hospital administration and the IT steering committee.

| # | SDLC Phase | Primary Output | Section |
| --- | --- | --- | --- |
| 1 | Planning | Objectives, stakeholders, schedule, budget | 3, 4, 5, 6 |
| 2 | Analysis | Requirements, feasibility, current-state workflow | 7 |
| 3 | Design | System architecture, workflow & data-flow design | 8 |
| 4 | Development | Configuration, integration, technical build-out | 9 |
| 5 | Testing | Beta trial, evaluation, QA sign-off | 10, 11 |
| 6 | Deployment & Maintenance | Go-live, installation setup, support plan | 12, 13 |

# 3. Team Members & Stakeholders

The project is delivered by a cross-functional team spanning hospital leadership, clinical staff, and the technical implementation partner. Table 3.1 lists each role and its primary responsibility; full job descriptions follow in Section 4.

## 3.1 Project Team Roster

| Role | Stakeholder Group | Reports To | Involvement |
| --- | --- | --- | --- |
| Project Sponsor | Hospital Administration | Board of Directors | Full project |
| Project Manager | IT / PMO | Project Sponsor | Full project |
| Clinical Lead (Ophthalmology) | Clinical | Medical Director | Analysis, Design, Testing, Go-live |
| AI/ML Solutions Architect | Technical Vendor | Project Manager | Analysis, Design, Development |
| Software Development Team (3–4 engineers) | Technical Vendor | Solutions Architect | Development, Testing |
| QA & Test Lead | Technical Vendor | Solutions Architect | Testing, QA |
| Hospital IT / Network Administrator | Hospital IT | IT Manager | Installation, Deployment, Maintenance |
| Data Privacy & Compliance Officer | Hospital Administration | Project Sponsor | Design, Testing, Deployment |
| Front-desk & Triage Nursing Staff | Clinical Operations | Clinical Lead | Testing (beta), Go-live, Maintenance |
| Training Coordinator | HR / Clinical Operations | Project Manager | Deployment |

# 4. Job Descriptions (JDs) of Each Stakeholder

### 4.1 Project Sponsor (Hospital Administration)

Reports to: Board of Directors

- Owns the business case and approves budget releases at each phase gate.

- Resolves cross-departmental conflicts and removes organisational blockers.

- Signs off on go-live readiness and accepts residual clinical risk.

### 4.2 Project Manager

Reports to: Project Sponsor

- Owns the project schedule, budget tracking and status reporting (Section 5, 6).

- Coordinates between the technical vendor, clinical staff and hospital IT.

- Runs weekly steering meetings and maintains the RAID (risks, assumptions, issues, dependencies) log.

### 4.3 Clinical Lead (Ophthalmology)

Reports to: Medical Director

- Defines clinical triage rules (emergency / urgent / routine criteria) with the AI architect.

- Validates that AI recommendations are clinically sound during beta testing.

- Trains and supervises doctors and nurses on when and how to override AI triage output.

### 4.4 AI/ML Solutions Architect

Reports to: Project Manager

- Designs the triage model pipeline: symptom intake, vitals ingestion, records lookup, classification logic.

- Specifies integration points with the Hospital Information System (HIS) and QR check-in kiosks.

- Owns model accuracy, explainability, and escalation-safety design (Section 8).

### 4.5 Software Development Team

Reports to: AI/ML Solutions Architect

- Builds and configures the booking/payment portal, QR check-in module, and triage dashboard.

- Implements the HIS/EMR integration and the doctor-facing override interface.

- Fixes defects raised during unit, integration, and beta testing.

### 4.6 QA & Test Lead

Reports to: AI/ML Solutions Architect

- Writes and executes the test plan (Section 10): functional, integration, load, and clinical-accuracy tests.

- Logs, triages and tracks defects to closure with the development team.

- Issues the formal QA sign-off required before go-live (Section 11).

### 4.7 Hospital IT / Network Administrator

Reports to: IT Manager

- Provisions on-site infrastructure: kiosks, network points, servers or cloud connectivity (Section 9, 12).

- Manages user accounts, access control and system uptime post-launch.

- First point of contact for Tier-1 support during the maintenance phase (Section 13).

### 4.8 Data Privacy & Compliance Officer

Reports to: Project Sponsor

- Reviews the system design against patient-data-protection obligations and hospital policy.

- Approves data-retention, access-logging and consent procedures before beta testing begins.

- Audits the system periodically post go-live.

### 4.9 Front-desk & Triage Nursing Staff

Reports to: Clinical Lead

- Operate the QR check-in and vitals-capture stations during beta and live operation.

- Provide day-to-day usability feedback used to refine the interface.

- Escalate any AI/system malfunction to Hospital IT immediately.

### 4.10 Training Coordinator

Reports to: Project Manager

- Develops training materials and runs onboarding sessions for clinical and front-desk staff.

- Tracks staff sign-off on training completion ahead of go-live.

- Coordinates refresher training after major system updates.

# 5. Timeline

The project is planned over an estimated 20-week schedule from kickoff to stabilised go-live, aligned to the six SDLC phases.

| Phase | Duration | Weeks | Key Milestone |
| --- | --- | --- | --- |
| Planning | 2 weeks | W1–W2 | Charter, budget & team sign-off |
| Analysis | 2 weeks | W3–W4 | Requirements & workflow baseline approved |
| Design | 3 weeks | W5–W7 | Architecture & UX design approved |
| Development | 6 weeks | W8–W13 | Feature-complete build (code freeze) |
| Testing (incl. Beta) | 4 weeks | W14–W17 | QA sign-off & beta evaluation report |
| Deployment | 2 weeks | W18–W19 | Go-live at pilot branch |
| Stabilisation / Hypercare | 1 week | W20 | Handover to steady-state maintenance |

A single-branch pilot go-live is recommended first, with a 4–6 week observation window before rollout to the remaining Hashmanis branches, to contain risk and validate real-world triage accuracy.

# 6. Cost Estimation

Figures below are planning-level estimates for a single-branch pilot deployment, in USD, for internal budgeting discussion — not a vendor quotation.

| Cost Category | Item | Estimated Cost (USD) |
| --- | --- | --- |
| Software | AI triage engine licensing / development (one-time) | 18,000 – 28,000 |
| Software | Booking & payment portal + QR check-in module | 8,000 – 12,000 |
| Integration | HIS / EMR integration & data pipeline | 6,000 – 10,000 |
| Hardware | Check-in kiosks, vitals devices, network gear (per branch) | 7,000 – 10,000 |
| Infrastructure | Cloud hosting / servers (annual) | 3,000 – 5,000 / yr |
| Testing | QA, beta trial & clinical validation | 4,000 – 6,000 |
| Training | Staff onboarding & materials | 1,500 – 2,500 |
| Maintenance | Support & updates (annual, from Year 1) | 5,000 – 8,000 / yr |
| Contingency | 10–15% of build cost | 4,000 – 7,000 |

Estimated pilot one-time cost: approximately USD 48,000 – 73,000, plus USD 8,000 – 13,000 in recurring annual hosting and support costs. Per-branch hardware and training costs recur for each subsequent branch rollout.

# 7. Analysis Phase

## 7.1 Current-State Workflow

Today, ophthalmic patients at Hashmanis Hospital move through manual booking, in-person payment, unstructured queuing, and doctor-led triage performed verbally at the start of each consultation. This creates two problems: urgent cases are not identified until they reach the front of a first-come-first-served queue, and administrative steps (payment, form-filling) consume clinical time that could be spent on patients.

## 7.2 Requirements Summary

### Functional Requirements

- Online booking with integrated payment.

- QR-code-based check-in linked to the patient's booking record.

- Automated vitals capture feeding directly into the patient record.

- AI triage engine producing an Emergency / Urgent / Routine label with supporting rationale.

- Doctor-facing dashboard allowing one-click confirm or override of the AI label.

- Real-time queue re-ordering based on triage label.

### Non-Functional Requirements

- Triage decision latency under 1 minute per patient (per case-study target).

- System availability of 99.5%+ during clinic hours.

- All patient data encrypted at rest and in transit; role-based access control.

- Audit trail for every AI recommendation and every doctor override.

- Usable by front-desk and nursing staff with under 2 hours of training.

## 7.3 Feasibility

- Technical: Hashmanis's existing HIS supports API-based integration; no core system replacement is required.

- Operational: Multi-branch structure makes Hashmanis a strong candidate — a single-branch pilot can validate the model before wider rollout.

- Clinical/Ethical: The AI is advisory only; a licensed doctor confirms or overrides every triage decision, keeping clinical accountability with a human at all times.

- Financial: Estimated cost (Section 6) is recoverable through reduced average visit time and higher patient throughput per branch.

# 8. Design Phase

## 8.1 The 7-Step AI-Assisted Workflow

The target-state patient journey, and the estimated duration of each step, is as follows:

| Step | Stage | Est. Duration | Owner |
| --- | --- | --- | --- |
| 01 | Online Booking & Payment | 2 min | Patient (self-service) |
| 02 | Travel & Parking | 6 min | Patient |
| 03 | QR Check-in & Vitals | 3 min | Front-desk / Nursing |
| 04 | AI Triage | < 1 min | AI System |
| 05 | Waiting | 3–5 min | — |
| 06 | Doctor Consultation | 8–10 min | Physician |
| 07 | Eye Tests (if needed) | 10–15 min | Clinical / Diagnostics |

Total estimated time: 23–27 minutes without diagnostic tests; 33–42 minutes with tests — down from the current manual baseline (see Section 8.3 for savings).

## 8.2 AI Decision Boundary — Where AI Decides vs Where the Doctor Decides

| Decision Point | Owner | Description |
| --- | --- | --- |
| Step 4 — AI Triage | AI System | Reads symptoms, vitals and records; labels the patient Emergency, Urgent or Routine and routes them automatically. |
| Step 6 — Doctor Consultation | Physician (Human required) | Specialist examines the patient, confirms or overrides the AI's triage label, diagnoses, and decides treatment. |

This split is a core design principle: the AI accelerates sorting and scheduling, but final clinical authority never leaves the treating physician.

## 8.3 Projected Time Savings

Savings are expected to come from three sources: online payment (removing an in-person billing step), QR check-in (removing manual registration), and parallel processing (triage running during/immediately after vitals capture rather than as a separate queued step).

| Visit Type | Time Saved per Visit |
| --- | --- |
| Without diagnostic tests | ~15–21 minutes |
| With diagnostic tests | ~20–36 minutes |

## 8.4 System Architecture (High Level)

- Patient-facing layer: booking/payment web portal, QR check-in kiosk, vitals capture device.

- Integration layer: API gateway connecting kiosks and vitals devices to the Hospital Information System (HIS).

- AI triage layer: rules-assisted classification model consuming structured symptom input, vitals, and historical records; outputs a label plus a short rationale for the doctor.

- Clinical layer: doctor dashboard showing incoming queue sorted by triage label, with one-tap confirm/override.

- Data layer: encrypted patient data store with full audit logging of AI outputs and human overrides.

# 9. Installation Setup & Technical Details of Each Step

This section details the technical build-out and on-premises installation required for each stage of the workflow.

### 9.1 Step 01–02 — Online Booking, Payment, Travel

- Deploy responsive booking web portal integrated with a licensed local payment gateway.

- Sync confirmed bookings to the HIS scheduling module via secure API.

- Send automated SMS/WhatsApp confirmation with a unique QR code per appointment.

### 9.2 Step 03 — QR Check-in & Vitals

- Install QR check-in kiosks (touchscreen, receipt printer optional) at hospital entrances.

- Connect digital vitals devices (BP, pulse, visual acuity pre-check where applicable) via Bluetooth/USB to the intake workstation.

- Vitals and check-in event write directly to the patient's record in real time.

### 9.3 Step 04 — AI Triage Engine

- Host the triage model on a secure on-premises server or approved cloud environment (per hospital data-residency policy).

- Configure the model's input schema: presenting symptoms (structured intake form), vitals, and relevant history from the EMR.

- Output: a triage label (Emergency / Urgent / Routine), a confidence indicator, and a short rationale string shown to the doctor.

- Define hard-coded safety overrides: any symptom on a pre-agreed 'red-flag' list is automatically escalated to Emergency, bypassing the model's confidence score.

### 9.4 Step 05–06 — Queue Management & Doctor Consultation

- Deploy a real-time queue dashboard in each consulting room, auto-sorted by triage label and check-in time.

- Doctor interface presents the AI label and rationale alongside the patient's chart; a single control lets the doctor confirm or override before proceeding.

- Every override is logged with the doctor's ID, timestamp and reason (for QA and compliance review).

### 9.5 Step 07 — Diagnostic Eye Tests

- Link diagnostic-equipment scheduling (where tests are indicated) into the same patient record so results flow back to the consulting doctor without re-entry.

## 9.6 Installation Sequence (Single Branch)

- Site survey and network readiness assessment.

- Install kiosks, vitals devices and network/POS hardware.

- Deploy server/cloud environment and configure the AI triage service.

- Integrate booking portal, kiosks and triage engine with the HIS via API.

- Configure user accounts and role-based access for all staff roles listed in Section 3.

- Run end-to-end smoke test of the full 7-step pipeline before opening to beta users.

# 10. Beta Version Testing & Evaluation

## 10.1 Test Levels

| Test Level | Scope | Owner |
| --- | --- | --- |
| Unit Testing | Individual modules: booking, payment, QR check-in, vitals capture | Development Team |
| Integration Testing | HIS ↔ kiosk ↔ triage engine ↔ doctor dashboard data flow | Development Team + QA Lead |
| Clinical Accuracy Testing | AI triage label vs. retrospective doctor-assigned severity on historical case samples | Clinical Lead + AI Architect |
| Load / Performance Testing | Peak-hour concurrent bookings and check-ins | QA Lead |
| Beta (Pilot) Testing | Live shadow-mode trial at one branch: AI runs alongside the existing manual process | Full project team |

## 10.2 Beta (Pilot) Evaluation Approach

The system runs in shadow mode for 2–3 weeks at the pilot branch: the AI produces a triage label for every patient, but the existing manual process continues in parallel so outcomes can be compared without patient risk.

- Compare AI triage labels against the doctor's independent assessment for every patient in the pilot window.

- Track false-negative escalations (AI under-triages a genuinely urgent case) as the top-priority metric — target: zero tolerated before go-live.

- Collect front-desk and nursing usability feedback on the kiosk and vitals workflow.

- Measure actual step-by-step timing against the projections in Section 8.1 and 8.3.

- Compile a Beta Evaluation Report summarising accuracy, timing, defects found, and staff feedback, submitted to the Project Sponsor as the go/no-go input for full go-live.

# 11. Quality Assurance

QA runs throughout Development and Testing (not as a single end-of-project step) and produces the formal sign-off required before deployment.

- Defect tracking: every issue logged with severity (Critical / High / Medium / Low) and owner; Critical and High defects must be closed before go-live.

- Clinical-safety QA gate: zero tolerated false-negative emergency escalations in the beta evaluation (Section 10.2).

- Data-privacy QA gate: sign-off from the Data Privacy & Compliance Officer confirming encryption, access control and audit logging meet policy.

- Usability QA gate: front-desk and nursing staff complete check-in and vitals capture within target time without escalation support.

- Formal QA sign-off document issued by the QA & Test Lead, co-signed by the Clinical Lead, ahead of the go-live decision in Section 5.

# 12. Deployment

## 12.1 Go-Live Approach

- Phase 1: Go-live at a single pilot branch with the AI triage engine fully live (no longer shadow mode).

- Hypercare period: project team on-site or on-call for the first 1–2 weeks to resolve issues in real time.

- Phase 2: Staged rollout to remaining Hashmanis branches after the pilot stabilises, reusing the hardware and integration templates from Section 9.

## 12.2 Cutover Checklist

- All Critical/High defects closed and QA sign-off obtained (Section 11).

- Beta Evaluation Report reviewed and approved by the Project Sponsor.

- All staff roles trained and sign-off collected (Training Coordinator, Section 4.10).

- Rollback plan documented: ability to revert to the manual process within one clinic day if required.

- Support contacts and escalation paths published to all clinical and front-desk staff.

# 13. Maintenance

## 13.1 Support Tiers

| Tier | Scope | Owner | Target Response |
| --- | --- | --- | --- |
| Tier 1 | Kiosk/device issues, basic user support | Hospital IT Administrator | < 30 minutes (clinic hours) |
| Tier 2 | Application/integration issues | Vendor support team | < 4 hours |
| Tier 3 | AI model issues, major incidents | AI/ML Solutions Architect | < 24 hours |

## 13.2 Ongoing Activities

- Quarterly review of AI triage accuracy against doctor overrides, led by the Clinical Lead, to identify drift or recurring disagreement patterns.

- Periodic data-privacy and access-log audit by the Compliance Officer.

- Scheduled software updates and security patching by the vendor support team, communicated in advance to Hospital IT.

- Refresher training for staff after any significant workflow or interface change.

- Annual cost and performance review against the estimates in Section 6 and the timing targets in Section 8.3.

# 14. Conclusion

This plan sets out a phased, SDLC-aligned path to installing an AI-assisted patient workflow at Hashmanis Hospital: automating booking, check-in and vitals capture, introducing an AI triage engine that keeps the treating doctor firmly in control, and targeting a 15–36 minute reduction in average visit time. A single-branch pilot with a shadow-mode beta period is recommended to validate clinical accuracy and staff usability before scaling across the hospital group, with quarterly accuracy review and a tiered support model to keep the system safe and effective over time.